## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2231-swen-261-03-team1
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a helper I want to see a list of needs so that I choose what to contribute to. | Given that I am on the u-fund site when I am not on the Needs page then I must see a means to navigate to the Needs page. | Pass | ADS; 10/22/2025
| Given that I am not on the Needs page when I choose the Needs page then I am taken to the Needs page. | Pass | ADS; 10/22/2025
| Given that I am on the Needs page when there are no needs in the cupboard I see a message indicating that that there are no needs available to contribute. | Pass | ADS; 10/22/2025
| Given that I am on the Needs page when there are needs in the cupboard then I see each need and short description. | Pass | ADS; 10/22/2025
| Given that I am on the Needs page when there are needs in the cupboard then I see a means to add each need to my funding basket. | Pass | ADS; 10/22/2025
As a helper I want to search for different needs so that I can more easily contribute to them. | Given that I am logged in as a user when I search for needs then I should get search results with all of the needs with matching names | Pass | ADS; 10/22/2025
| Given that I am logged in as a user when I search for needs then I should get no results if there is no need with matching names | Pass | ADS; 10/22/2025
As an admin I want to update my needs so that I can make changes and corrections to my needs. | Given that I am logged in as an Admin when I attempt to edit a need then I expect that need to update be updated for everyone | Pass | ADS; 10/22/2025
As an admin I want to delete outdated needs so that people can fund current ones and not waste their money. | Given the Need exists when I delete the need then the Need should be removed and unavailable for others to see and access. | Pass | ADS; 10/22/2025
As a helper I want to add needs to my basket so that I can easily curate a list of needs that I want to support. | Given I am logged in as a helper when I add a need to my basket then I expect to see that need in my basket | Pass | ADS; 10/22/2025
As a helper I want to log in and out so that other users cannot access my basket. | Given I correctly enter my username and password as a helper when I am logged out and trying to log in then I should be logged into my helper account. | Pass | ADS; 10/22/2025
As an admin I want to create new needs so that others can contribute to them. | Given I am logged in as an admin when I create the Need then the Need should appear in my cupboard. | Pass | ADS; 10/22/2025
As an admin I want to log in and out so that other users cannot utilize my elevated permissions. | Given I correctly enter my username and password as an admin when I am logged out and trying to log in *then I should be logged into my admin account. | Pass | ADS; 10/22/2025
As a helper I want to checkout my basket so that finalize my contributions to the selected needs. | Given I am logged in as a helper when I checkout my basket then my money will go towards the needs I checked out. | Pass | ADS; 10/22/2025
As a product owner I want to have a persistent inventory so that the system stays up to date. | Given I create, update, or delete a need when I am logged in as an admin then the changes should be reflected in everyone's inventory. | Pass | ADS; 10/22/2025
As a helper I want to have persistent basket so that I can access it across multiple sessions. | Given I add something to my basket when I am logged in, then I want that need to save so that it may appear again when I log-in in a different session. | Pass | ADS; 10/22/2025